## User Cases
# | Feature | Use case | Student | Teacher | Guest | CRDD Staff | Designer | Admin | CRDD Head | Use case description
1 | User Access | View home page before and after login | x | x | x | x | x | x | x | The user access the website and views the page without being logged in. After logging in, based on the user's role in the hamepage will be displayed with the corresponding functions.
2 | User Access | Register new account | x | x |  | x | x |  |  | Users will register a new account by email or phone number
3 | User Access | Login to the system | x | x | x | x | x | x | x | Users use a pre-registered account to log in or use a google account to log in
4 | User Access | Reset password | x | x | x | x | x | x | x | When the user forgets the password, it is necessary to enter the email or phone number to get the verification code to be able to change the password
5 | User Access | Update user profile | x | x | x | x | x | x | x | Users view their personal information: avatar, name, email, phone number, ... and can change personal information when necessary, except email and phone number cannot be changed.
6 | User Access | Change password | x | x | x | x | x | x | x | Change the password when the user feels it is necessary
7 | System Admin | View list account | [5 empty] | x |  | Admin can view all accounts saved in the system
8 | System Admin | View account details | [5 empty] | x |  | Admin view all information of a certain user and can change that person's role
9 | System Admin | View setting list (view master data) | [5 empty] | x |  | Admin see the master data in the system, can be the whole or the data is searched by name, type
10 | System Admin | Edit setting infor (edit master data) | [5 empty] | x |  | Admin edits a certain master data when have incorrect information
11 | Curriculum Management | View Curriculum List | x | x | x | x | x | x | x | Users view the entire curriculum in the system
12 | Curriculum Management | Add New Curriculum |  |  |  | x |  |  | x | Admin adds new curriculums at the beginning of each school year to the system
13 | Curriculum Management | View Curriculum Overview | x | x | x | x | x | x | x | Show an overview of a particular curriculum so that users can better understand that curriculum.
14 | Curriculum Management | Edit Curriculum |  |  |  | x |  |  | x | Admin will change the necessary information of the curriculum to match the actual changes
15 | Subject Management | View Subject List |  |  |  | x |  |  | x | Show the subjects that have been added to the system
16 | Subject Management | Add New Subject |  |  |  | x |  |  | x | Admin adds new subject into the system
17 | Subject Management | Import Subject |  |  |  | x |  |  | x | Admin will import the excel file containing subject information to the system
18 | Subject Management | View Subject Detail | x | x | x | x | x | x | x | Show information of a certain subject
19 | Subject Management | Mapping Subject-PLO | [7 empty] | Show the relationship between PLO and subject in each curriculum
20 | Subject Management | View Subject Predecessors | x | x | x | x | x | x | x | The user knows the predecessors of a certain subject
21 | Subject Management | View Subject Successors | x | x | x | x | x | x | x | The user knows the successors of a certain subject
22 | Curriculum Subject | View Curriculum Subject Details | x | x | x | x | x | x | x | View the subjects included in a certain curriculum in the system
23 | Curriculum Subject | Add New Curriculum Subject |  |  |  | x |  |  | x | Admin adds subjects to curriculum
24 | PLO Management | View PLO List | x | x | x | x | x | x | x | Show the list of program learning outcomes available in the system
25 | PLO Management | View PLO Details | x | x | x | x | x | x | x | Show the detail of a certain program learning outcome
26 | PLO Management | Import PLO |  |  |  | x |  |  | x | Admin import program learning outcomes into the system
27 | PLO Management | Mapping PLO-PO | x | x | x | x | x | x | x | Show the relationship between PLO and PO in each curriculum
28 | PO Management | View PO List | x | x | x | x | x | x | x | Show the list of PO available in the system
29 | PO Management | Import PO |  |  |  | x |  |  | x | CRDD Staff import PO into the system
30 | PO Management | View PO Detail | x | x | x | x | x | x | x | Show the detail of a certain PO
31 | Subject Groups | View Combo List | x | x | x | x | x | x | x | Show the list of Combo available in the system
32 | Subject Groups | View Combo Detail | x | x | x | x | x | x | x | Show, edit the detail of a certain Combo
33 | Subject Groups | View Content Group List | x | x | x | x | x | x | x | Show the list of Content Group available in the system
34 | Subject Groups | View Content Group Details | x | x | x | x | x | x | x | Show, edit the detail of a certain Content Group
35 | Subject Groups | View Elective List | x | x | x | x | x | x | x | Show the list of Elective available in the system
36 | Subject Groups | View Elective Details | x | x | x | x | x | x | x | Show, edit the detail of a certain Elective
37 | Syllabus Management | View Syllabus List | x | x | x | x | x | x | x | Show the list of Syllabus available in the system
38 | Syllabus Management | View Syllabus Overview | x | x | x | x | x | x | x | Show an overview of a Syllabus so that users can better understand that Syllabus.
39 | Syllabus Management | Add New Syllabus |  |  |  |  | x |  | x | Designer design and add new syllabus
40 | Syllabus Management | Edit Syllabus |  |  |  |  | x |  | x | Review check syllabus then edit if necessary
41 | Syllabus Management | Import Syllabus |  |  |  | x | x |  | x | Designer import Syllabus into the system
42 | Decision Management | View Decision List | x | x | x | x | x | x | x | Show the list of Decision available in the system
43 | Decision Management | View Decision Details | x | x | x | x | x | x | x | Show detail of decision
44 | Decision Management | Add New Decision | [6 empty] | x | CRDD Head make new decisions
45 | Decision Management | View Decision Overview | x | x | x | x | x | x | x | Show an overview of a Decision so that users can better understand that Decision.
46 | Syllabus Submit | View Submit List |  |  |  | x | x | x | x | Show the list of Submit available in the system
47 | Syllabus Submit | View Submit Details |  |  |  | x | x | x | x | Show detail of Submit
48 | Constructive Questions | View Question List | x | x | x | x | x | x | x | Show the list of Question available in the system
49 | Constructive Questions | View Question Details | x | x | x | x | x | x | x | Show detail of Question
50 | Constructive Questions | Import Question |  |  |  | x | x |  | x | Designer import Question into the system
51 | Session Management | View Session List | x | x | x | x | x | x | x | Show the list of Session available in the system
52 | Session Management | View Session Details | x | x | x | x | x | x | x | Show detail of Session
53 | Session Management | Import Session |  |  |  | x | x |  | x | Designer import Session into the system
54 | CLO Management | View CLO List | x | x | x | x | x | x | x | Show the list of CLO available in the system
55 | CLO Management | View CLO Detail | x | x | x | x | x | x | x | Show detail of CLO
56 | CLO Management | Import CLO |  |  |  | x | x |  | x | Designer import CLO into the system
57 | CLO Management | Mapping CLO-PLO |  |  |  | x | x |  | x | Show the relationship between PLO and CLO in each curriculum
58 | Assessment Management | View Assessment List | x | x | x | x | x | x | x | Show the list of Assessment available in the system
59 | Assessment Management | View Assessment Details | x | x | x | x | x | x | x | Show detail of Assessment
60 | Reference Material | View Material List | x | x | x | x | x | x | x | Show the list of Material available in the system
61 | Reference Material | View Material Details | x | x | x | x | x | x | x | Show detail of Material

## Product
# | Feature | Screen/Function | User WF | Curriculum WF | Decision WF | Syllabus WF | Screen/Function Details | In Charge | Status | SRS | SDS | Planned | Actual | Updated | Update Details
1 | User Access | Home Page | X | X | X | X | View homepage: - Get some basic infor | Tạ Ngọc Quân | Done | II.1.a | II.1-1.1 | iter1 |  |  | Đã Show được ảnh default khi chưa có ảnh Hoàn thiện màn hình UI dễ sử dụng hơn
2 | User Access | User Register | X |  |  |  | Register new account: - Input information of new account - Get email or phone number of new user - Insert that data into database of system | Tạ Ngọc Quân | Done | II.1.b | II.1-1.2 | iter1 |  |  | khi lỗi input các giá trị đã nhập sẽ không bị reset nữa Không send được mail thì đã báo lỗi Mã hóa được mật khẩu khi đăng khí Register with phone đã tích hợp được fire base Show toast khi đăng kí thành công vả trả về login luôn
3 | User Access | User Login | X | X | X | X | Login to website: - Input account/email/phone number and password - Check that account correct or not | Nguyễn Việt Trung | Done | II.1.c | II.1-1.3 | iter1 | iter1 |  | Demo Home Page. Login google đã lấy được profile.
4 | User Access | Password Reset | X |  |  |  | Reset password: - Input mail/phone number - Send, check verification code - Set new password | Nguyễn Việt Trung | Done | II.1.d | II.1-1.4 | iter1 | iter1 |  | Reset password with phone (Firebase). Show toast và về luôn login khi reset thành công Đã Cải thiện UI , mã hóa MK
5 | User Access | User Profile | X |  |  |  | View user profile: - View - Update information - Send, check verification code when add mail or mobile | Nguyễn Trung Quân | Done | II.1.e | II.1-1.5 | iter1 |  |  | Đã check unique Username Upload ảnh mới cần xóa ảnh cũ Đã validate inputs
6 | User Access | Password Change | X |  |  |  | Change password: - Input old, new password - Check - Update new password | Nguyễn Trung Quân | Done | II.1.f | II.1-1.6 | iter1 |  |  | Ko reset fields nếu sai inputs Show toast và về luôn Login khi thay đổi password thành công
7 | System Admin | Account List | X |  |  |  | View account list: - Filter - Search - View | Nguyễn Tất Khoa | Done | II.2.a | II.7 | iter1 |  |  | Đã có phân trang và khóa mềm, có post thông báo
8 | System Admin | Account Detail | X |  |  |  | View account detail: - View information of a account - Update role | Nguyễn Tất Khoa | Done | II.2.b | II.2-2.1 | iter1
9 | System Admin | Setting List | X |  |  |  | View setting list: - Filter - Search - View | Lê Văn Tiến | Done | II.2.c | II.2-2.2 | iter1
10 | System Admin | Setting Detail | X |  |  |  | View detail setting: - View detail master date - Update | Lê Văn Tiến | Done | II.2.d | II.2-2.3 | iter1
11 | Curriculum Management | Curriculum List |  | X |  |  | View Curriculum List: - Search - View | trungnvhs160609 | Done | II.3.a | II.3-3.1 | iter2 |  |  | Update search (no,name ko cần chọn) Đã Thêm cột Status + status filter Cột Actions đã thêm tiêu đề cột + activate/deativate action Đã thêm Filter active + deactivate
12 | Curriculum Management | New Curriculum |  | X |  |  | Add New Curriculum: - Insert - View - Check | trungnvhs160609 | Done | II.3.c | II.3-3.2 | iter2 |  |  | Đã bỏ show Decision Id; Update Owner thay bằng Assignee combo-box và cho phép user chọn, Description ko bắt buộc, để dưới Asignee name & code đã có * trong label Đã check độ dài Code bị trùng ko reset đi.
13 | Curriculum Management | Curriculum Overview |  | X |  |  | View Curriculum Overview: - View | trungnvhs160609 | Done | II.3.b | II.3-3.3 | iter2 |  |  | Đã chỉnh lại UI: page title; field size SubHeader ko ẩn khi cuộn xuống Decision code không hiển thị <br>
14 | Curriculum Management | Curriculum Edit |  | X |  |  | Edit Curriculum: - Update - Check - View | quantnhe161199 |  | II.3.d | II.3-3.4 | iter2 |  |  | Đã show được decision theo fomat và không cho sửa Đã thay show owner Assignee và bổ sung creator Phân quyền theo Role chỉ người tạo và admin phân công cho ai người đó mới được sửa Đã check length và check null cho code và name các trường name và code đã thêm dấu * đỏ để đánh dấu
15 | Subject Management | Subject List |  | X |  |  | View Subject List: - Search - View - Filter | quannthe160206 | Done | II.4.a | II.4-4.1 | iter2 |  |  | Đã sửa phần search, UI Đã bổ sung cột Actions: edit, activate/deactivate
16 | Subject Management | New Subject |  | X |  |  | Add New Subject: - Insert - Check - View | quannthe160206 | Done | II.4.b | II.4-4.2 | iter2 |  |  | Đã bỏ: type, parent, group Chỉ để Code, Name, Status, Desc Check length
17 | Subject Management | Subject Import |  | X |  |  | Import Subject: - Upload file - Insert - Check | quannthe160206 | Done | II.4.c | II.4-4.3 | iter2 |  |  | Đã thêm phần tải tệp mẫu Các cột Excel giống New Subject Đã xử lý khi import hiện ra các dòng import thành công và những dòng bị lỗi cùng lỗi
18 | Subject Management | Subject Detail |  | X |  |  | View Subject Detail: - View - Edit | quannthe160206 | Done | II.4.d | II.4-4.4 | iter2 |  |  | Thêm phần edit Show predecessors
19 | Subject Management | Subject-PLO Mapping |  | X |  |  | Mapping Subject-PLO: - Insert - View - Check | khoanthe161852 | Done | II.4.e | II.4-4.5 | iter2 |  |  | Đã hoàn thành
20 | Subject Management | Subject Predecessors |  | X |  |  | View Subject Predecessors: - Insert -View | khoanthe161852 | Done | II.4.f | II.4-4.6 | iter2 |  |  | Đã sử dụng đúng câu lệnh truy vấn và lấy ra 3 đời của subject prrcessors
21 | Subject Management | Subject Successors |  | X |  |  | View Subject Successors: - Insert -View | khoanthe161852 | Done | II.4.g | II.4-4.7 | iter2 |  |  | Đã sử dụng đúng câu lệnh truy vấn và lấy ra 3 đời của subject Successors
22 | Curriculum Subject | Curriculum Subject Details |  | X |  |  | View Curriculum Subject Details: - View | quantnhe161199 | Done | II.6.a | II.6-6.1 | iter2 |  |  | Đã show PreRequisite
23 | Curriculum Subject | New Curriculum Subject |  | X |  |  | Add New Curriculum Subject: - View - Insert - Check | quantnhe161199 | Done | II.6.b | II.6-6.2 | iter2
24 | PLO Management | PLO List |  | X |  |  | View PLO List: - View - Search | tienlvhe161878 | Done | II.5.a | II.5-5.1 | iter2
25 | PLO Management | PLO Details |  | X |  |  | View PLO Details: - View - Edit | tienlvhe161878 | Done | II.5.b | II.5-5.2 | iter2
26 | PLO Management | PLO Import |  | X |  |  | Import PLO: - Upload file - Insert - Check | tienlvhe161878 Trung Quân | Done | II.5.c | II.5-5.3 | iter2 | iter3 |  | Đã xử lý khi import hiện ra các dòng import thành công và những dòng bị lỗi cùng lỗi
27 | PLO Management | PLO-PO Mapping |  | X |  |  | Mapping PLO-PO: - Insert - View - Check | Khoa | Done | II.5.d | II.5-5.4 | iter3
28 | PO Management | PO List |  | X |  |  | View PO List: - View - Search | Khoa | Done | II.7.a | II.7-7.1 | iter3 |  |  | Bổ xung filter theo status Để nút add và import sang bên trái và filter bên phải Dùng icon phù hợp
29 | PO Management | PO Import |  | X |  |  | Import PO: - Upload file - Insert - Check | Khoa | Done | II.7.b | II.7-7.2 | iter3
30 | PO Management | PO Detail |  | X |  |  | View PO Details: - View - Edit | Khoa | Done | II.7.c | II.7-7.3 | iter3 |  |  | Check trùng name trong curriculum Giới hạn độ dài trường descrepsion
31 | Subject Groups | Cur Combo List |  | X |  |  | View Combo List: - View - Search | Ngọc Quân | Done | II.8.a | II.8-8.1 | iter3 |  |  | Đã thêm xác nhận nếu nhấn xóa Đã cải thiện Ui Không show curriculum
32 | Subject Groups | Cur Combo Detail |  | X |  |  | View Combo Details: - View - Edit | Ngọc Quân | Done | II.8.b | II.8-8.2 | iter3 |  |  | Đã không thêm các trường type và curiculum ở new Đã hiển thị các danh sách subject ở trong 1 combo
33 | Subject Groups | Content Group List |  | X |  |  | View Content Group List: - View - Search | Trung Quân | Done | II.8.c | II.8-8.3 | iter3 |  |  | Thêm yêu cầu xác nhận khi xóa
34 | Subject Groups | Content Group Details |  | X |  |  | View Content Group Details: - View - Edit | Trung Quân | Done | II.8.d | II.8-8.4 | iter3 |  |  | Thêm cột Description (text-area) Ko cho add subject khi edit, khi xóa người dùng cần confirm
35 | Subject Groups | Elective List |  | X |  |  | View Elective List: - View - Search | Ngọc Quân | Done | II.8.e | II.8-8.5 | iter3 |  |  | không show curriculum nữa khi xóa cần phải comfirm mới được xóa
36 | Subject Groups | Elective Details |  | X |  |  | View Elective Details: - View - Edit | Ngọc Quân | Done | II.8.f | II.8-8.6 | iter3 |  |  | đã show các trường group content,subject_code,subject_name bên trong Elective muốn xóa subject trong elective phải comfirm
37 | Syllabus Management | Syllabus List |  |  |  | X | View Syllabus List: - View - Search - Filter | Tiến | Done | II.9.a | II.9-9.1 | iter3
38 | Syllabus Management | Syllabus Overview |  |  |  | X | View Syllabus Overview: - View | Tiến | Done | II.9.b | II.9-9.2 | iter3
39 | Syllabus Management | New Syllabus |  |  |  | X | Add Syllabus Subject: - View - Insert - Check | Tiến | Done | II.9.c | II.9-9.3 | iter3
40 | Syllabus Management | Syllabus Edit |  |  |  | X | Edit Syllabus: - Update - Check - View | Tiến | Done | II.9.d | II.9-9.4 | iter3
41 | Decision Management | Decision List |  |  | X |  | View Decision List: - View - Search - Filter | Trung | Done | II.10.a | II.10-10.1 | iter3 |  |  | Đã Format date, thêm cột creator Đã search được theo Name Đã cho xóa, sort Đã hiển thị cho xóa/sửa riêng với staff
42 | Decision Management | Decision Details |  |  | X |  | View Decision Details: - View - Edit | Trung | Done | II.10.b | II.10-10.2 | iter3 |  |  | creator đã show name đã ẩn date khi edit
43 | Decision Management | New Decision |  |  | X |  | Add Decision : - View - Insert - Check | Trung | Done | II.10.c | II.10-10.3 | iter3 |  |  | đã chỉnh ko show create_date & creator_id đã thêm * vào label các trường bắt buộc
44 | Decision Management | Decision Overview |  |  | X |  | View Decision Overview: - View | Trung | Done | II.10.d | II.10-10.4 | iter3 |  |  | Đã format date Đã lọc quyền view của Guest
45 | Constructive Questions | Question List |  |  |  | X | View Question List: - View - Search - Filter | Trung | Done | II.12.a | II.12-12.1 | iter4
46 | Constructive Questions | Question Details |  |  |  | X | View Question Details: - View - Edit | Trung | Done | II.12.b | II.12-12.2 | iter4
47 | Constructive Questions | Question Import |  |  |  | X | Import Question: - Upload file - Insert - Check | Trung | Done | II.12.c | II.12-12.3 | iter4
48 | Session Management | Session List |  |  |  | X | View Session List: - View - Search - Filter | Ngọc Quân | Done | II.13.a | II.13-13.1 | iter4
49 | Session Management | Session Details |  |  |  | X | View Session Details: - View - Edit | Ngọc Quân | Done | II.13.b | II.13-13.2 | iter4
50 | Session Management | Session Import |  |  |  | X | Import Session: - Upload file - Insert - Check | Ngọc Quân | Done | II.13.c | II.13-13.3 | iter4
51 | CLO Management | CLO List |  |  |  | X | View CLO List: - View - Search - Filter | khoa | Done | II.14.a | II.14-14.1 | iter4
52 | CLO Management | CLO Detail |  |  |  | X | View CLO Details: - View - Edit | khoa | Done | II.14.b | II.14-14.2 | iter4
53 | CLO Management | CLO Import |  |  |  | X | Import CLO : - Upload file - Insert - Check | khoa | Done | II.14.c | II.14-14.3 | iter4
54 | CLO Management | CLO-PLO Mapping |  |  |  | X | Mapping CLO-PLO: - Insert - View - Check | khoa | Done | II.14.d | II.14-14.4 | iter4
55 | Assessment Management | Assessment List |  |  |  | X | View Assessment List: - View - Search - Filter | tiến | Done | II.15.a | II.15-15.1 | iter4
56 | Assessment Management | Assessment Details |  |  |  | X | View Assessment Details: - View - Edit | tiến | Done | II.15.b | II.15-15.2 | iter4
57 | Reference Material | Material List |  |  |  | X | View Material List: - View - Search - Filter | tiến | Done | II.16.a | II.16-16.1 | iter4
58 | Reference Material | Material Details |  |  |  | X | View Material Details: - View - Edit | tiến | Done | II.16.b | II.16-16.2 | iter4
59 | Syllabus Management | Syllabus Import |  |  |  | X | Import Syllabus : - Upload file - Insert - Check | Trung Quân | Done | II.9.e | II.9-9.5 | iter4

## Iter1
# | Screen / Function | In Charge | Status | Notes
1 | Home Page | Tạ Ngọc Quân | Done
2 | User Register | Tạ Ngọc Quân | Done
3 | User Login | Nguyễn Việt Trung | Done
4 | Password Reset | Nguyễn Việt Trung | Done
5 | User Profile | Nguyễn Trung Quân | Done
6 | Password Change | Nguyễn Trung Quân | Done
7 | Account List | Nguyễn Tất Khoa | Done
8 | Account Detail | Nguyễn Tất Khoa | Done
9 | Setting List | Lê Văn Tiến | Done
10 | Setting Detail | Lê Văn Tiến | Done

## Iter2
# | Screen / Function | In Charge | Status | Notes
1 | Curriculum List | trungnvhs160609 | Done
2 | New Curriculum | trungnvhs160609 | Done
3 | Curriculum Overview | trungnvhs160609 | Done
4 | Subject List | quannthe160206 | Done
5 | New Subject | quannthe160206 | Done
6 | Subject Import | quannthe160206 | Done
7 | Subject Detail | quannthe160206 | Done
8 | Curriculum Subject Details | quantnhe161199 | Done
9 | New Curriculum Subject | quantnhe161199 | Done
10 | Curriculum Edit | quantnhe161199 | Done
11 | Subject-PLO Mapping | khoanthe161852 | Doing
12 | Subject Predecessors | khoanthe161852 | Done
13 | Subject Successors | khoanthe161852 | Done
14 | PLO List | tienlvhe161878 | Done
15 | PLO Details | tienlvhe161878 | Done
16 | PLO Import | tienlvhe161878 | Doing

## Iter3
# | Screen / Function | In Charge | Status | Notes
1 | PO List | khoa | Done
2 | PO Import | khoa | Done
3 | PO Detail | khoa | Done
4 | PLO-PO Mapping | khoa | Done
5 | Combo List | Ngọc Quân | Done
6 | Combo Detail | Ngọc Quân | Done
7 | Content Group List | Trung Quân | Done
8 | Content Group Details | Trung Quân | Done
9 | Elective List | Ngọc Quân | Done
10 | Elective Details | Ngọc Quân | Done
11 | Decision List | Trung | Done
12 | Decision Details | Trung | Done
13 | New Decision | Trung | Done
14 | Decision Overview | Trung | Done
15 | PLO import | Trung Quân | Done
16 | Syllabus List | Tiến | Done
17 | Syllabus Overview | Tiến | Done
18 | New Syllabus | Tiến | Done
19 | Syllabus Edit | Tiến | Done

## Iter4
# | Screen / Function | In Charge | Status | Notes
1 | Submit List | Trung Quân | To-do
2 | Submit Details | Trung Quân | To-do
3 | Question List | Trung | Done
4 | Question Details | Trung | Done
5 | Question Import | Trung | Done
6 | Session List | Ngọc Quân | Done
7 | Session Details | Ngọc Quân | Done
8 | Session Import | Ngọc Quân | Done
9 | CLO List | khoa | Done
10 | CLO Detail | khoa | Done
11 | CLO Import | khoa | Done
12 | CLO-PLO Mapping | khoa | Done
13 | Assessment List | tiến | Done
14 | Assessment Details | tiến | Done
15 | Material List | tiến | Done
16 | Material Details | tiến | Done
17 | Syllabus Import | Trung Quân | Done
18 | Subject-PLO Mapping | khoa | Doing